## RICs
Type | Cause | Effect | Impact | Likelihood | Importance | Response type | Response | Custodian | Dates
[9 empty] | Identification | Occurrence | Closure
R | A system test failure | May have to go back to the drawing board. Have to debug code and stop testing till it's done correctly | 75 | 60 | 2 | Reduce | Code to be backed up in-case of failure resulting in loss of code. Tests to be dynamic so that code can be quickly changed to fix errors and tested within a few minutes | Ross | 2023-02-06
R | Ovverun costs | Means that the project would run at a deficiet, would frustrate the client | 40 | 5 | 1 | Avoid | Project to be kept within budget | George | 2023-02-06
R | Wrong deliverables | Wrongly interpreted the specification, would cause problems with the client/sponsor | 60 | 20 | 1 | Avoid | A deliverables map to be created and the key deliverables to be the main things delivered at the end of the project | George | 2023-02-06
R | Project overruns | Means that the project would not meet its hard deadline | 75 | 15 | 1 | Reduce | Project to be kept on time. Implementation of concept only to occur if there is time available | George | 2023-02-06
R | Loss of code | The project would be delayed and would mean that it would have to be built again | 95 | 60 | 2 | Watch | Code to be backed up on GitHub. Development server (separate) from GitHub to be used for testing | Ross | 2023-02-06
R | Client wants to adjust the scope | Would push the progress back, frustrate the team | 50 | 0 | 1 | Accept | As we are a student project, this is not going to happen | George | 2023-02-06
R | Design plans not to client request | Would frustrate the client. Project may not be accepted by the client | 55 | 0 | 1 | Accept | As we are a student project, this is not going to happen | George | 2023-02-06
R | No access to database servers | Would make the project untestable and mostly unworkable | 100 | 25 | 1 | Accept | This is a risk we cannot do anything about | Ross | 2023-02-06
R | Copyright infringement | Would get the team in trouble with the Academic Integrity Officer | 65 | 10 | 1 | Avoid | All media used in the project will be checked for its copyright before it is used | George | 2023-02-06
R | University don't allow the testing on infrastructure | Would mean that the team cannot go beyond the proof of concept model | 10 | 50 | 1 | Accept | This is a risk we cannot do anything about | George | 2023-02-06
R | Lack of resources | Would mean that the team cannot go beyond the proof of concept model | 50 | 10 | 1 | Avoid | This is a risk we cannot do anything about | George | 2023-02-06
R | Natural disaster | Would completely decimate the project making it unworkable | 100 | 1 | 1 | Accept | This is a risk we cannot do anything about | George | 2023-02-06
R | Covid-19 Lockdown | Would make the project untestable and mostly unworkable, but if this was to occur at an early stage, it may be possible to pull off the concept | 90 | 1 | 1 | Accept | This is a risk we cannot do anything about | George | 2023-02-06
R | Illness | Would reduce the team's ability to effectively do work, highly depends on which team member falls ill | 15 | 50 | 1 | Accept | This is a risk we cannot do anything about | George | 2023-02-06
R | University network failure | Would completely decimate the project making it unworkable | 100 | 1 | 1 | Accept | This is a risk we cannot do anything about | Ross | 2023-02-06
R | Cyber attack/loss of critical infrastructure | Would completely decimate the project making it unworkable | 100 | 2 | 1 | Accept | This is a risk we cannot do anything about | Ross | 2023-02-06
R | Plagerism | Would mean that the project would be under the scrutiny of the Academic Integrity Officer and would make it difficult to complete the project due to stress | 90 | 7 | 1 | Avoid | All sources to be properly referenced in code, designs and reports | Ross | 2023-02-06
Note on A1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: One of R = Risk I = Issue C = Change
Note on B1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Short text to explain the source of the RIC
Note on C1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Short text describing the effect of the RIC
Note on D1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Percentage rating of the impact of the risk on the project where 0 is negligible and 100 is disastrous.
Note on E1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Percentage rating of the likelihood of the risk where 0 is impossible and 100 is certain.
Note on F1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This value is calculated from impact and likelihood and colour-coded.
Note on G1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: One of Accept, Avoid, Mitigate, Transfer, Monitor
Note on H1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Short text describing the action planned (R) or taken (IC)
Note on I1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Name of the person who is responsible for monitoring the RIC until it is closed
Note on J2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Date that the RIC was identified
Note on K2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Date that the RIC occurred
Note on L2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Date that the RIC was closed

## Profile
Impact
High | 8 | 2 | 0
Medium | 5 | 0 | 0
Low | 0 | 2 | 0
| Low | Medium | High | Likelihood

## Help
Help information |  |  | R | Accept
|  |  | I | Avoid
This file is used for recording and controlling risks, issues and changes (RICs) and should be reviewed and updated regularly. These terms are defined below. |  |  | C | Reduce
Transfer
Risk | A hypothetical event that might occur in the future and which would affect the project |  |  | Watch
Issue | An actual event that occurs and which requires some action to be taken
Change | A (potential) modification to the project definition after it has been finalised
Please refer to the notes below which described the contents of the fields on the main sheet.
Field | Required for | Description
Cause | RIC | Short text to explain the source of the RIC
Effect | RIC | Short text describing the effect of the RIC
Impact | R | Percentage rating of the impact of the risk on the project where 0 is negligible and 100 is disastrous.
Liklihood | R | Percentage rating of the likelihood of the risk where 0 is impossible and 100 is certain.
Significance | Calculated | This value is calculated from impact and likelihood and colour-coded
Response type | R | One of Accept, Avoid, Reduce, Transfer, Watch
Response | RIC | Short text describing the action planned (R) or taken (IC)
Custodian | RIC | Name of the person who is responsible for monitoring the RIC until it is closed
Identification | RIC | Date that the RIC was identified
Occurrence | RIC | Date that the RIC occurred
Closure | RIC | Date that the RIC was closed